## Pre-Production Summary
Project Name | Watch
Total Estimated Assets & Implementation Times | (See other sheets for breakdowns)
Total Model Time: | 12.4
Total Rigging and Animation Time: | 5.8
Total Scripting Time: | 25.1
Total VFX Time: | 22.4
Total SFX Time: | 26.6
Total UI Time: | 21.7
Total Time: | 114
Scale
Unit Size:
Notes:
Unknowns

## Models
Models | Category | Model Time | UV Map Time | Texture Time | LightingTime | Approval/Adjustment Time | Total Time For Model
Low-Res Models
Watch Body | Small | 5 Minutes |  | 0 | 0.3 | 0 | 0.3
Watch Brackets | Small | 6 Minutes |  | 0 | 0.5 | 2 | 2.5
Watch Band Upper | Small | 4 Minutes |  | 0 | 0.5 | 1 | 1.5
Watch Band Lower | Small | 4 Minutes |  | 0 | 1 | 0.5 | 1.5
0
|  |  |  | 0 |  | Total Low-Res Model Time: | 5.8
Medium-Res Models |  |  |  | 0
Watch Body | Small | 10 Minutes |  | 0 | 0.2 | 0.2 | 0.4
Watch Face | Small | 4 Minutes |  | 0 | 0.2 | 0.2 | 0.4
Watch Brackets | Small | 4 Minutes |  | 0 | 0.2 | 0.2 | 0.4
Watch Knob | Small | 3 Minutes |  | 0 | 0.2 | 0.2 | 0.4
Watch Back Hax | Small | 2 Minutes |  | 0 | 0.5 | 0.2 | 0.7
Watch Band Upper | Small | 20Minutes |  | 0 | 0.2 | 0.2 | 0.4
Watch Band Lower | Small | 15 Minutes |  | 0 | 0.2 | 0.2 | 0.4
Watch Buckle & Spine | Small | 25 Minutes |  | 0 | 0.2 | 0.2 | 0.4
Watch Spindle Upper | Small | 2 Minutes |  | 0 | 0.3 | 0.2 | 0.5
Watch Spindle Lower | Small | 2 Minutes |  | 0 | 0.2 | 0.2 | 0.4
| Small | 0 Minutes |  | 0 | 0.2 | 0.2 | 0.4
| Small | 0 Minutes |  | 0 | 0.2 | 0.2 | 0.4
| Small | 0 Minutes |  | 0 | 0.2 | 0.2 | 0.4
| Small | 0 Minutes |  | 0 | 0.4 | 0.2 | 0.6
| Small | 0 Minutes |  | 0 | 0.2 | 0.2 | 0.4
[6 empty] | Total Medium-Res Model Time: | 6.6
High-Res Models
Watch Body | Small | 5 Minutes | 20 Minutes |  |  |  | 0
Watch Face | Small | 4 Minutes | 8 Minutes |  |  |  | 0
Watch Brackets | Small | 7 Minutes | 13 Minutes |  |  |  | 0
Watch Knob | Small | 2 Minutes | 5 Minutes |  |  |  | 0
Watch Back Hax | Small | 2 Minutes | 4 Minutes |  |  |  | 0
Watch Band Upper | Small | 20 Minutes | 80 Minutes |  |  |  | 0
Watch Band Lower | Small | 15 Minutes | 30 Minutes |  |  |  | 0
Watch Buckle & Spine | Small | 10 Minutes | 15 Minutes |  |  |  | 0
Watch Spindle Upper | Small | 2 Minutes | 3 Minutes |  |  |  | 0
Watch Spindle Lower | Small | 2 Minutes | 3 Minutes |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
| Small | 0 Minutes |  |  |  |  | 0
[6 empty] | Total High-Res Model Time: | 0
[6 empty] | Total Model Time: | 12.4

## Rigging and Animation
Model To Animate | Category | Rig Time | Animation Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Animation
Characters
BabaYagaHut | Large | 3 | 1 | 0.5 | 0.3 | 1 | 5.8
[6 empty] | Total Character Animation Time: | 5.8
[6 empty] | Total Rig & Animation Time: | 5.8

## Scripts
Scripts | Category | Coding Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Script
Player
PlayerMovement | Medium | 2 | 0.5 | 0.5 | 1 | 4
CameraControl | Small | 1 | 0.3 | 0.2 | 1 | 2.5
Jump | Small | 1 | 0.3 | 0.2 | 2 | 3.5
[5 empty] | Total Player Script Time: | 10
Game Events
GameReset | Small | 1 | 0.3 | 0.2 | 0.5 | 2
PlayerDeath | Small | 1 | 0.2 | 0.1 | 0.5 | 1.8
CollectItem | Medium | 2 | 0.5 | 0.5 | 1 | 4
[5 empty] | Total Events Script Time: | 7.8
Rendering
CullingObjects | Small | 1 | 0.2 | 0.2 | 1 | 2.4
TexReplacer(?) | Medium | 2 | 0.4 | 0.5 | 2 | 4.9
[5 empty] | Total Rendering Script Time: | 7.3
[5 empty] | Total Script Time: | 25.1

## VFX
VFX | Category | Art/Script Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For VFX
Camera
Shake | Medium | 0.3 | 1.5 | 0.3 | 1 | 3.1
Collect | Small | 0.3 | 1 | 0.2 | 1 | 2.5
Death | Medium | 0.3 | 1 | 0.3 | 1 | 2.6
[5 empty] | Total Camera VFX Time: | 8.2
Environmental
Fog | Large | 2 | 2 | 0.4 | 1 | 5.4
[5 empty] | Total Environmental VFX Time: | 5.4
Event
WoodCrack | Small | 1 | 1 | 0.5 | 0.5 | 3
DustPoof | Small | 1 | 1 | 0.5 | 0.5 | 3
CollectSparkle | Small | 1 | 1 | 0.3 | 0.5 | 2.8
[5 empty] | Total Event VFX Time: | 8.8
[5 empty] | Total VFX Time: | 22.4

## SFX
SFX | Category | Recording/Editing Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For SFX
Player
Damage | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Jump | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Landing | Small | 0.3 | 1 | 0.2 | 0.5 | 2
HeavyLanding | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Death | Medium | 1 | 1 | 0.2 | 1 | 3.2
[5 empty] | Total Player SFX Time: | 11.2
Environmental
BackgroundCreaks | Large | 2 | 1 | 0.5 | 1 | 4.5
BabaYagaHutStomp | Medium | 0.5 | 2 | 0.5 | 1 | 4
[5 empty] | Total Environmental SFX Time: | 8.5
Event
WoodCrack | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
DustPoof | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
CollectSparkle | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
[5 empty] | Total Event SFX Time: | 6.9
[5 empty] | Total SFX Time: | 26.6

## UI
UI | Category | Art/Scripting Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For UI
Camera
CrackScreen | Medium | 2 | 2 | 0.2 | 0.5 | 4.7
Collectable | Small | 1 | 1 | 0.2 | 0.5 | 2.7
FadeScreen | Small | 0.3 | 2 | 0.2 | 1 | 3.5
[5 empty] | Total Camera UI Time: | 10.9
Front End
TitleScreen | Large | 2 | 1 | 0.5 | 1 | 4.5
[5 empty] | Total Front End UI Time: | 4.5
Pause
PauseMenu | Large | 3 | 2 | 0.3 | 1 | 6.3
[5 empty] | Total Pause UI Time: | 6.3
[5 empty] | Total UI Time: | 21.7